## Work Plan
Kgfsl Spring MVC Framework Work Plan
ID | Module | Task/Screen/Menu | Task Description | Status | Start | Finish | Responsibility | Remarks
1 |  | Project Setup | Create basic Project setup in Spring STS IDE along with below features : 1. Maven 2. JUnit 3. Git SCM | Completed | 2014-04-21 | 2014-05-05 | Karthik
|  | Template Design | Template design for web application compatible with most modern browsers. Target browser versions :- Internet Explorer - 8+ Firefox - 17+ Chrome - Latest | Completed | 2014-05-05 | 2014-05-08 | Vidyaganesh | Used Ace Template (bootstrap)
|  | Tiles Setup | Tiles setup with the Ace Template | Completed | 2014-05-07 | 2014-05-08 | Karthik | Theme support to be added
|  | Custom Components | Create custom reusable components to be used across all screens, a) Form controls with custom validators b) Customizable Grid component | Pending
2 | Common Screens | Login Screen | Capture User Id & Password to allow authorized user. | Completed | 2014-05-06 | 2014-05-09 | Vidyaganesh
|  | Change Password | a) Capture New Password & Confirm Password b) Password policy & Encryption standards | Pending
|  | Security features | Implement standard Security features, a) XSS, CSRF, SQL injection, etc attack fixes on all screens b) Role-based authentication for all pages c) Session management, Form input validations, Error handling, Logging & configuration. | Pending
3 | Admin Console | Menu | Capture menu order, name, code, description, active flag | In Progress | 2014-05-12 |  | Vidyaganesh
|  | User | a) Capture user informations as follows: - Full name, Date Of Birth, Login Id, Role, Email, Mobile No. Address, Active Flag. b) Provision to reset user's password. c) Provision to lock/unlock user's access. | In Progress | 2014-05-12 |  | Vidyaganesh
|  | Role | Capture role code, role name, active flag | In Progress | 2014-05-12 |  | Karthik
|  | Role - Menu mapping | Enable dynamic role-based access | In Progress | 2014-05-12 |  | Karthik
|  | Preferences / Lookup Master | Common settings menu | In Progress | 2014-05-12 |  | Thangaraju
4

## Portal Plan (hidden)
Tech Assist Portal Development Plan
ID | Prolive ID | Task Description | Duration (in days) | % Completed | Status | Start | Finish | Responsibility